Overall Roadmap and Resource Plan

Activate AI Platform – AI Gateway and AI Apps Platform

Phased Deliverables (Activate format)

Prepared by: Activate Interactive Pte Ltd

Release: 1.5 (Draft for review) – supply-chain trust for AI-assisted delivery (signed SBOM, build provenance, AI-BOM; RESPONSIBLE-AI backlog BL-01 and BL-02, 3 October 2026) added as a section 5 backlog row and to the 1.3 mapping; section 5 total recalculated; sections 2–4 unchanged; 1.4: additions (†) from the RESPONSIBLE-AI-ENTERPRISEREADY roadmap review (2 October 2026): gateway admin console, scoped gateway settings, AI App–AI Gateway integration contract with build-time credentials and token exchange, guided configuration and configuration copilot, LiteLLM capability discovery, admin audit view; dedicated proxy per silo tenant added to the backlog; mapping in section 1.3; sections 2–5 recalculated; 1.3: Activate team second revision: Phase 0 gateway items (provider abstraction to cache analytics) set to 0 MD; Phase 1 generic knowledge and analytics tools set to 8 MD (2 / 1 / 5); sections 3–5 recalculated and reviewed; 1.2: section 2.1 revised by the Activate team (scope moves and per-feature design and testing), reviewed and carried through all sections; LiteLLM detailed design additions (†) re-estimated against the revised items; Phases 3–4 re-estimated where LiteLLM provides the capability; 1.1: Phase 0 additions; 1.0: first issue

Date: 3 October 2026

Author(s): Joseph Stephen, Solutions Architect

Sources: Activate Roadmap Timeline slide (Phases 0–4); AI Gateway Recommended Architecture v1.7; AI App Platform Recommended Architecture v1.5; AI Gateway LiteLLM Detailed Design v1.1; RESPONSIBLE-AI-ENTERPRISEREADY roadmap and Proxy Manager enterprise design (2 Oct 2026); RESPONSIBLE-AI supply-chain trust proposal, SUPPLY_CHAIN_TRUST.md (3 Oct 2026)

# 1  Purpose and Method

This document combines the AI Gateway and the AI Apps Platform into one phased roadmap and projects the resources each phase needs. Chart 1 is the roadmap; Chart 2 is the resource requirement, given as tables.

| Rule | Applied as |
| --- | --- |
| Features and effort | Phases 0–2: the Activate team’s revision of section 2.1 (October 2026). Phases 3–4: proposed breakdown (marked *), re-estimated where LiteLLM already provides the capability. Additions beyond the slide are marked †. |
| Design, development and testing | Per feature, as entered by the Activate team for Phases 0–2 and for additions. Each phase’s “Continuous architecture, design, testing” line keeps its own design, development and testing split. Where a row’s discipline figures and its total disagreed, the discipline figures were used (section 1.1). |
| Product management | Not on the slide; added at 10% of each phase’s effort. |
| Product attribution | G = AI Gateway, A = AI Apps Platform, S = shared platform core (split 50/50). Continuous design and testing is split in proportion to each product’s effort in the phase. |
| Team size | FTE = phase MD ÷ 20 working days (one month per phase). |

## 1.1  Review of the Revised Section 2.1

The Activate team revised the phase scope and figures in section 2.1. The revision was reviewed row by row; the table lists every change and how it was resolved. All other sections are recalculated from the result.

| # | Change or finding | Resolution |
| --- | --- | --- |
| 1 | Phase 0 item 1 widened to the platform core for both products (data models, tenant management, AI App–AI Gateway integration, tenant and admin portal for both). Labelled AI Apps. | Accepted. Re-tagged Shared core (50/50) because it serves both products. Disciplines 4 / 13 / 4 = 21 MD (the row showed 20). |
| 2 | Phase 0 gateway items 2–8 (provider abstraction to cache analytics) set to 0 MD for design, development and testing (second revision). | Accepted: delivered as LiteLLM configuration. The only Phase 0 gateway effort is now the LiteLLM tenant integration row (†, 8 MD) – see the risk in section 4. |
| 3 | Phase 0 continuous line 6 design / 6 testing (12 MD). | Accepted. |
| 4 | Phase 1: Business Service Builder named as Activepieces, 4 / 9 / 4 = 17 MD; generic knowledge and analytics tools moved into Phase 1 without figures. | Accepted. Generic tools set by the Activate team to 8 MD (2 design / 1 development / 5 testing), replacing the 23 MD review estimate – see the risk in section 4. |
| 5 | Phase 1 gateway items with per-feature testing; budget controls 5 MD; usage export 2 MD; continuous line 3 / 2 / 3. | Accepted. |
| 6 | Phase 2: LangGraph agentic workflows (10) and an agentic batch-processing app (10, shared) replace the NEA port and the tenant portal; continuous line 3 / 2 / 4. | Accepted. Continuous line = 9 MD (the row showed 10). The tenant portal is now in Phase 0 item 1; the NEA port moves to Phase 4. |
| 7 | Phase 3 environment promotion raised from 5 to 8 MD. | Accepted. |
| 8 | Phase 4: NEA Training Simulator port moved in without figures; the agent–workflow interoperability rows (added in the previous release) were missing from the edited copy. | NEA port sized at the slide value, 10 MD (7 / 3). Interoperability rows restored (9 MD, †). |
| 9 | Possible overlap: Phase 2 “LangGraph agentic workflows” and Phase 4 “Agents – agent runtime and templates”. | Kept both. To confirm: if Phase 2 delivers the agent runtime, Phase 4 can be reduced to templates (about −5 MD). |

## 1.2  Effort Revisited

| Item | Previous | Now | Why |
| --- | --- | --- | --- |
| LiteLLM tenant integration build (Phase 0, †) | 1.5 MD (net over 16 MD slide development) | 8 MD (6.5 dev, 1.5 test) | Unchanged. It was sized when the Phase 0 gateway rows carried 11 MD development; those rows are now 0 MD, so this row is the only Phase 0 effort for the gateway capabilities. The detailed design estimates 17.5 MD development for them (section 4). |
| Runtime-to-gateway trust (Phase 0, †) | 1.5 MD | 2 MD (1.5 dev, 0.5 test) | Per-feature testing added, matching the revised convention. |
| As-built cache hardening (†) | 3.5 MD in Phase 0 | 4.5 MD in Phase 2 (3.5 dev, 1 test) | Moved to Phase 2: the L1 cache only needs to scale once more tenants onboard, and Phase 0 is already the second-largest phase. |
| Prompt-injection detection (Phase 3) | 6 MD | 4 MD | LiteLLM ships heuristic and LLM-based detection plus Lakera, Bedrock and Presidio integrations. |
| Semantic routing (Phase 4) | 6 MD | 4 MD | LiteLLM Auto Router (beta) covers classification and keyword routing; effort is configuration plus evaluation. |
| Re-ranking for RAG (Phase 4) | 4 MD | 2 MD | The as-built RAG already re-ranks; route it through LiteLLM /rerank for one cost ledger. |
| Testing uplift (Phase 3, †) | 25 MD Horizon 1 “quality uplift” (rationalisation) | 6 MD in Phase 3 | Phases 0–2 carry per-feature testing; design and testing are about 38% of feature effort. Only Phase 3 stays thin, so the uplift is reduced and placed there. |

## 1.3  Additions from the RESPONSIBLE-AI-ENTERPRISEREADY Roadmap Review

The RESPONSIBLE-AI-ENTERPRISEREADY project (reference implementation of the LiteLLM proxy manager, metering and FinOps / AIOps on AWS) was reviewed on 2 October 2026 and its roadmap requirements were mapped onto Phases 0–4. Requirements already covered by an Activate row are noted as covered; the rest are added as † rows with proposed estimates for the Activate team’s review. Estimates follow the AI-assisted convention of this plan; the gateway admin console, DB-managed runtime configuration and key rotation exist as verified code, so the console is sized as a port to the Activate core (Entra ID roles, organisation model).

| Requirement (RESPONSIBLE-AI roadmap) | Where it lands in Phases 0–4 | MD (†) | Resolution |
| --- | --- | --- | --- |
| LiteLLM forward proxy for all chat; usage metering; FinOps and AIOps dashboards (built) | Phase 0 rows 2–8 (LiteLLM configuration); Phase 1 budget controls, usage export; observability | – | Covered; reference implementation on ECS Fargate, Aurora and Cognito available to port |
| Multi-provider model management (Groq, Bedrock, Anthropic, OpenAI …) with credentials in Secrets Manager or LiteLLM’s encrypted store | Phase 1 row 5 (provider configuration) plus new row 10 gateway admin console | 6 | New † row (port of the Proxy Manager) |
| Every LiteLLM setting definable by an administrator (router, callbacks, cache, general settings), runtime configuration held in the proxy database, key rotation | Phase 1 row 10 gateway admin console | incl. | Verified 2 Oct 2026 in the reference implementation |
| Tenant → LiteLLM team mapping; per-tenant configuration and credential store | Phase 0 row 9 LiteLLM tenant integration build | – | Covered |
| Settings per tenant → department → application with narrow-only inheritance | Phase 2 row 6 scoped gateway settings | 8 | New † row |
| AI App control plane ↔ AI Gateway: runtime discovery, gateway-granted authentication, no service without a grant | Phase 0 rows 1 and 10 (integration, runtime-to-gateway trust) plus new Phase 0 row 11 integration contract and Phase 3 row 8 credentials, token exchange and events | 4 + 6 | New † rows |
| Examples, best practice and validation for configuration; AI-assisted guidance | Phase 2 row 7 guided configuration; Phase 4 row 8 configuration copilot | 5 + 8 | New † rows |
| New LiteLLM capabilities surfaced without a platform release | Phase 2 row 8 LiteLLM capability discovery | 4 | New † row |
| Audit view of gateway configuration changes | Phase 3 row 9 admin audit view | 2 | New † row |
| Response caching on ElastiCache with per-tenant namespaces | Phase 0 rows 6–8 (LiteLLM configuration); Phase 2 cache hardening | – | Covered; Terraform module and cache panel designed (RESPONSE_CACHING.md) |
| Tenant data separation (row-level security), tenant-scoped policies, guardrails, MCP and reports | Phase 0 recommended security fixes; Phase 3 governance | – | Covered |
| Evaluation platform (Ragas, TruLens) off the request path | Phase 3 row 4 evaluations | – | Covered |
| Chargeback and showback by tenant, team and application | Phase 1 usage export / billing; FinOps | – | Covered |
| Dedicated LiteLLM proxy per tenant (isolation tier T2) | Section 5 backlog | 12 | New backlog row |
| Supply-chain trust: signed SBOM, SLSA build provenance, VEX and AI-BOM for every release on a reproducible build (recorded in the RESPONSIBLE-AI backlog as BL-01 and BL-02, 3 October 2026) | Section 5 backlog | 11 | New backlog row |

# 2  Chart 1 – Phased Roadmap

Figure 1 – Overall phased roadmap, AI Gateway (G) and AI Apps Platform (A) with shared core (S)

## 2.1  Phase Scope by Feature and Discipline

### Phase 0 – Enable AI Application Platform, Resilience & Caching (Nov-26)

| # | Feature | Product | Design | Development | Testing | Product mgmt | Total MD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Architect & build AI Application and AI Gateway platform core: data models, tenant management, loosely coupled integration between AI App and AI Gateway; tenant and admin portal for both | Shared core | 4 | 13 | 4 | – | 21 |
| 2 | Provider abstraction | AI Gateway | 0 | 0 | 0 | – | 0 |
| 3 | Model failover | AI Gateway | 0 | 0 | 0 | – | 0 |
| 4 | Circuit breaker | AI Gateway | 0 | 0 | 0 | – | 0 |
| 5 | Timeout configuration | AI Gateway | 0 | 0 | 0 | – | 0 |
| 6 | Semantic cache | AI Gateway | 0 | 0 | 0 | – | 0 |
| 7 | Cache TTL and tenant isolation | AI Gateway | 0 | 0 | 0 | – | 0 |
| 8 | Cache analytics | AI Gateway | 0 | 0 | 0 | – | 0 |
| 9 | LiteLLM tenant integration build (tenancy sync to teams and keys; uplift for tenant namespace, cache policy and per-tenant analytics) † | AI Gateway | 0 | 6.5 | 1.5 | – | 8 |
| 10 | Runtime-to-gateway trust (app gateway key + signed context token) † | Shared core | 0 | 1.5 | 0.5 | – | 2 |
| 11 | AI App–AI Gateway integration contract: /.well-known/ai-gateway discovery document and authenticated capability manifest (sections, routes, scopes, JSON Schemas) for runtime discovery; tenant onboarding as the gateway grant † | Shared core | 1 | 2 | 1 | – | 4 |
| 12 | Continuous architecture, design, testing | Shared (continuous) | 6 | 0 | 6 | – | 12 |
|  | Product management (10% of phase effort) | Programme | – | – | – | 4.7 | 4.7 |
|  | Phase total |  | 11 | 23 | 13 | 4.7 | 51.7 |

### Phase 1 – Multi-Provider + Monetization (Dec-26)

| # | Feature | Product | Design | Development | Testing | Product mgmt | Total MD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | App platform – port GRL@PA app, generic and template-driven | AI Apps | 0 | 7 | 0 | – | 7 |
| 2 | App platform – Business Service Builder (UI-driven workflow tool, Activepieces) | AI Apps | 4 | 9 | 4 | – | 17 |
| 3 | Generic knowledge and analytics tools: generalise the as-built RAG and QuickSight dashboards / publishing for any app (connectors via Activepieces pieces) | AI Apps | 2 | 1 | 5 | – | 8 |
| 4 | Multi-modal support | AI Gateway | 0 | 1 | 1 | – | 2 |
| 5 | Provider configuration and management | AI Gateway | 0 | 1 | 2 | – | 3 |
| 6 | Provider health monitoring | AI Gateway | 0 | 2 | 2 | – | 4 |
| 7 | Basic routing algorithms | AI Gateway | 0 | 3 | 2 | – | 5 |
| 8 | Granular budget controls | AI Gateway | 1 | 3 | 1 | – | 5 |
| 9 | Usage export / billing integration | AI Gateway | 0 | 1 | 1 | – | 2 |
| 10 | Gateway admin console (Proxy Manager): providers, models and prices, credentials (Secrets Manager or LiteLLM encrypted store), keys and teams with budgets and rotation, MCP servers, proxy guardrails, routing / fallback / cache / general settings held in the proxy database; audited, allow-listed passthrough – port of the RESPONSIBLE-AI reference implementation † | AI Gateway | 0.5 | 4 | 1.5 | – | 6 |
| 11 | Continuous architecture, design, testing | Shared (continuous) | 3 | 2 | 3 | – | 8 |
|  | Product management (10% of phase effort) | Programme | – | – | – | 6.7 | 6.7 |
|  | Phase total |  | 10.5 | 34 | 22.5 | 6.7 | 73.7 |

### Phase 2 – Self-Serve + Developer Experience (Jan-27)

| # | Feature | Product | Design | Development | Testing | Product mgmt | Total MD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | LangGraph agentic workflows | AI Apps | 0 | 7 | 3 | – | 10 |
| 2 | App platform – Business Service Builder support for MCP and agents | AI Apps | 0 | 10 | 5 | – | 15 |
| 3 | MCP provider integration to AI Gateway | AI Gateway | 0 | 4 | 1 | – | 5 |
| 4 | Agentic app for batch processing | Shared core | 0 | 7 | 3 | – | 10 |
| 5 | As-built cache hardening (Valkey exact tier, HNSW index, purge, upsert, single embedding, tenant quotas) † | AI Gateway | 0 | 3.5 | 1 | – | 4.5 |
| 6 | Scoped gateway settings: org → department → app → key with narrow-only inheritance and locks; scope switcher in the admin console; mapped to LiteLLM organization / team / key (router settings, guardrails, tags, callbacks, budgets) † | AI Gateway | 1 | 5 | 2 | – | 8 |
| 7 | Guided configuration: settings catalogue with recommended values per environment and workload, pre-save validation, configuration profiles with diff preview † | AI Gateway | 1 | 3 | 1 | – | 5 |
| 8 | LiteLLM capability discovery: manifest from /routes and OpenAPI, coverage status, upgrade diff with audit, admin-enabled allow-list (inference routes excluded), schema-driven explorer † | AI Gateway | 0 | 3 | 1 | – | 4 |
| 9 | Continuous architecture, design, testing | Shared (continuous) | 3 | 2 | 4 | – | 9 |
|  | Product management (10% of phase effort) | Programme | – | – | – | 7.1 | 7.1 |
|  | Phase total |  | 5 | 44.5 | 21 | 7.1 | 77.6 |

### Phase 3 – Enterprise Trust (Feb-27)

| # | Feature | Product | Design | Development | Testing | Product mgmt | Total MD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Governance – policy lifecycle and approvals * | AI Gateway | 0 | 7 | 0 | – | 7 |
| 2 | Compliance evidence (IM8, NIST AI RMF, SOC 2 controls) * | AI Gateway | 0 | 6 | 0 | – | 6 |
| 3 | Prompt-injection detection (LiteLLM built-in detection and guardrail integrations) * | AI Gateway | 0 | 3 | 1 | – | 4 |
| 4 | Evaluations (offline and online) * | AI Gateway | 0 | 7 | 0 | – | 7 |
| 5 | Policy as code * | AI Gateway | 0 | 5 | 0 | – | 5 |
| 6 | Environment promotion (dev → test → prod for apps, prompts, policies) | Shared core | 0 | 8 | 0 | – | 8 |
| 7 | Testing uplift for enterprise-trust features (policy, compliance, evaluation test suites) † | AI Gateway | 0 | 0 | 6 | – | 6 |
| 8 | Build-time and run-time app credentials (client credentials for CI, SDK and evaluation pipelines), gateway token exchange for the App control plane acting for a tenant administrator, gateway events (webhooks / EventBridge) † | Shared core | 1 | 4 | 1 | – | 6 |
| 9 | Admin audit view: gateway configuration changes (providers, models, keys, settings, rotations, seeding) with tenant scope † | AI Gateway | 0 | 1.5 | 0.5 | – | 2 |
| 10 | Continuous architecture, design, testing * | Shared (continuous) | 1.6 | 0 | 2.4 | – | 4 |
|  | Product management (10% of phase effort) | Programme | – | – | – | 5.5 | 5.5 |
|  | Phase total |  | 2.6 | 41.5 | 10.9 | 5.5 | 60.5 |

### Phase 4 – Scale & Differentiation (Mar-27)

| # | Feature | Product | Design | Development | Testing | Product mgmt | Total MD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Disaster recovery (backup, restore, multi-AZ runbooks) * | Shared core | 0 | 6 | 0 | – | 6 |
| 2 | Semantic routing (LiteLLM Auto Router, beta) * | AI Gateway | 0 | 3 | 1 | – | 4 |
| 3 | Re-ranking for RAG (as-built reranker routed through LiteLLM /rerank) * | AI Gateway | 0 | 1.5 | 0.5 | – | 2 |
| 4 | Agents – agent runtime and templates * | AI Apps | 0 | 10 | 0 | – | 10 |
| 5 | App platform – port Training Simulator app (NEA), generic and template-driven | AI Apps | 0 | 7 | 3 | – | 10 |
| 6 | Workflow Agent – expose LangGraph agents to Activepieces flows (Invoke Agent action; agents as MCP tools) † | AI Apps | 0 | 4 | 1 | – | 5 |
| 7 | Agent Workflow – LangGraph agents call Activepieces flows as tools via the Activepieces MCP server † | AI Apps | 0 | 3 | 1 | – | 4 |
| 8 | Configuration copilot: propose-only assistant grounded in the settings catalogue, LiteLLM docs, effective configuration and FinOps / AIOps signals; reviewable diffs applied only after approval; evaluated with Ragas † | AI Gateway | 1 | 5 | 2 | – | 8 |
| 9 | Continuous architecture, design, testing * | Shared (continuous) | 1.6 | 0 | 2.4 | – | 4 |
|  | Product management (10% of phase effort) | Programme | – | – | – | 5.3 | 5.3 |
|  | Phase total |  | 2.6 | 39.5 | 10.9 | 5.3 | 58.3 |

# 3  Chart 2 – Resource Requirement by Phase

## 3.1  Both Products

| Discipline | Phase 0 (Nov-26) | Phase 1 (Dec-26) | Phase 2 (Jan-27) | Phase 3 (Feb-27) | Phase 4 (Mar-27) | Total MD |
| --- | --- | --- | --- | --- | --- | --- |
| Design (architecture, solution and UX design) | 11 | 10.5 | 5 | 2.6 | 2.6 | 31.7 |
| Development | 23 | 34 | 44.5 | 41.5 | 39.5 | 182.5 |
| Testing (QA, automation, performance, security) | 13 | 22.5 | 21 | 10.9 | 10.9 | 78.3 |
| Product management | 4.7 | 6.7 | 7.1 | 5.5 | 5.3 | 29.3 |
| Total | 51.7 | 73.7 | 77.6 | 60.5 | 58.3 | 321.8 |
| Indicative team (FTE over 20 working days) | 2.6 | 3.7 | 3.9 | 3 | 2.9 | 3.2 |

## 3.2  By Product

| Product | Phase 0 | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total MD |
| --- | --- | --- | --- | --- | --- | --- |
| AI Gateway (incl. share of shared core, design, testing, PM) | 32.1 | 33.2 | 38 | 52.5 | 19.7 | 175.5 |
| AI Apps Platform (incl. share of shared core, design, testing, PM) | 19.6 | 40.5 | 39.6 | 8 | 38.6 | 146.3 |
| Total | 51.7 | 73.7 | 77.6 | 60.5 | 58.3 | 321.8 |

### AI Gateway – by discipline

| Discipline | Phase 0 (Nov-26) | Phase 1 (Dec-26) | Phase 2 (Jan-27) | Phase 3 (Feb-27) | Phase 4 (Mar-27) | Total MD |
| --- | --- | --- | --- | --- | --- | --- |
| Design (architecture, solution and UX design) | 6.3 | 2.7 | 3 | 2 | 1.4 | 15.4 |
| Development | 14.8 | 15.8 | 22.7 | 35.5 | 12.5 | 101.3 |
| Testing (QA, automation, performance, security) | 8.1 | 11.7 | 8.8 | 10.2 | 4 | 42.8 |
| Product management | 2.9 | 3 | 3.5 | 4.8 | 1.8 | 16 |
| Total | 32.1 | 33.2 | 38 | 52.5 | 19.7 | 175.5 |
| Indicative team (FTE over 20 working days) | 1.6 | 1.7 | 1.9 | 2.6 | 1 | 1.8 |

### AI Apps Platform – by discipline

| Discipline | Phase 0 (Nov-26) | Phase 1 (Dec-26) | Phase 2 (Jan-27) | Phase 3 (Feb-27) | Phase 4 (Mar-27) | Total MD |
| --- | --- | --- | --- | --- | --- | --- |
| Design (architecture, solution and UX design) | 4.7 | 7.8 | 2 | 0.6 | 1.2 | 16.3 |
| Development | 8.2 | 18.2 | 21.8 | 6 | 27 | 81.2 |
| Testing (QA, automation, performance, security) | 4.9 | 10.8 | 12.2 | 0.7 | 6.9 | 35.5 |
| Product management | 1.8 | 3.7 | 3.6 | 0.7 | 3.5 | 13.3 |
| Total | 19.6 | 40.5 | 39.6 | 8 | 38.6 | 146.3 |
| Indicative team (FTE over 20 working days) | 1 | 2 | 2 | 0.4 | 1.9 | 1.5 |

## 3.3  Team by Role and Phase

Indicative full-time equivalents for a one-month phase (20 working days). Roles map to disciplines: design → solution architect and UX designer; development → engineers; testing → QA engineers; product management → product manager.

| Role | Phase 0 (Nov-26) | Phase 1 (Dec-26) | Phase 2 (Jan-27) | Phase 3 (Feb-27) | Phase 4 (Mar-27) | Average |
| --- | --- | --- | --- | --- | --- | --- |
| Solution architect / UX designer (design) | 0.6 | 0.5 | 0.3 | 0.1 | 0.1 | 0.3 |
| Engineers – gateway and apps (development) | 1.2 | 1.7 | 2.2 | 2.1 | 2 | 1.8 |
| QA / test engineers (testing) | 0.7 | 1.1 | 1.1 | 0.5 | 0.5 | 0.8 |
| Product manager (product management) | 0.2 | 0.3 | 0.4 | 0.3 | 0.3 | 0.3 |
| Total FTE | 2.6 | 3.7 | 3.9 | 3 | 2.9 | 3.2 |

Phases 0–4 total about 321.8 MD (182.5 development, 31.7 design, 78.3 testing, 29.3 product management) – about 3.2 FTE on average for five months (peak 3.9 FTE in Phase 2), with development at about 57% of total effort. Of this, 47.3 MD (43 MD of features plus product management) are the additions from the RESPONSIBLE-AI roadmap review (section 1.3).

# 4  Reconciliation, Risks and Recommendations

| Phase | Slide header MD | Itemised MD used | Difference | Note |
| --- | --- | --- | --- | --- |
| Phase 0 | 50 | 47 | -3 | Revised by the Activate team: platform core for both products incl. tenant management and the tenant and admin portal; gateway items 2–8 (provider abstraction to cache analytics) set to 0 MD as LiteLLM configuration. Plus † LiteLLM tenant integration build (8 MD) and runtime–gateway trust (2 MD). Plus † from the RESPONSIBLE-AI-ENTERPRISEREADY roadmap review (2 October 2026): AI App–AI Gateway integration contract (4 MD) |
| Phase 1 | 52 | 67 | 15 | Revised by the Activate team: per-feature testing; generic knowledge and analytics tools moved in at 8 MD (2 / 1 / 5). Plus † gateway admin console – Proxy Manager (6 MD, port of the RESPONSIBLE-AI reference implementation) |
| Phase 2 | 50 | 70.5 | 20.5 | Revised by the Activate team: LangGraph agentic workflows and an agentic batch-processing app replace the NEA port (moved to Phase 4) and the tenant portal (moved to Phase 0). Plus † as-built cache hardening (4.5 MD). Plus † scoped gateway settings (8 MD), guided configuration (5 MD) and LiteLLM capability discovery (4 MD) |
| Phase 3 | 40 | 55 | 15 | Breakdown proposed (*); environment promotion 8 MD per the Activate team; prompt-injection detection revised to 4 MD (LiteLLM built-in detection). Plus † testing uplift (6 MD). Plus † app credentials, token exchange and gateway events (6 MD) and admin audit view (2 MD) |
| Phase 4 | 30 | 53 | 23 | Breakdown proposed (*); semantic routing revised to 4 MD and re-ranking to 2 MD (LiteLLM Auto Router and /rerank); NEA port moved in (10 MD). Plus † agent–workflow interoperability (9 MD). Plus † configuration copilot (8 MD) |

- Additions (†) from the LiteLLM detailed design: LiteLLM tenant integration build (8 MD) and runtime-to-gateway trust (2 MD) in Phase 0; as-built cache hardening (4.5 MD) in Phase 2.

- Additions (†) from the RESPONSIBLE-AI-ENTERPRISEREADY roadmap review (2 October 2026), 43 MD of feature effort plus 4.3 MD product management: integration contract (Phase 0, 4 MD); gateway admin console (Phase 1, 6 MD); scoped gateway settings, guided configuration and LiteLLM capability discovery (Phase 2, 17 MD); app credentials, token exchange and events plus admin audit view (Phase 3, 8 MD); configuration copilot (Phase 4, 8 MD). The estimates are proposals for the Activate team’s review. Risk: Phase 2 becomes the peak phase (3.9 FTE); if that is too high, the LiteLLM capability discovery row (4 MD) can move to Phase 3 and the guided-configuration row (5 MD) to Phase 4 alongside the copilot.

- Risk – Phase 0 gateway capabilities: provider abstraction, failover, circuit breaker, timeouts, semantic cache, cache TTL and tenant isolation, and cache analytics are now 0 MD. Only the LiteLLM tenant integration row (8 MD: 6.5 development, 1.5 testing) remains. The detailed design needs about 6.5 MD development for LiteLLM deployment and configuration (ECS service, Valkey, Bedrock IAM, failover, cooldowns, timeouts, Prometheus) on top of 11 MD of tenant integration, plus testing. Recommendation: confirm that the 8 MD row is meant to cover this, or add back about 6.5 MD development and 3 MD testing.

- Risk – generic knowledge and analytics tools (Phase 1, 8 MD with 1 MD development): enough to expose the as-built RAG search as a tool, but generalising the QuickSight authoring, embedding and publishing (now GRL@PA-specific) to pluggable data sources was estimated at about 15 MD. Recommendation: confirm the scope (for example knowledge tool in Phase 1, analytics generalisation later) or raise the development estimate.

- Critical security fixes from the AI Gateway as-built review (committed secrets, row-level security not enforced) are not on the slide. Recommend adding about 8 MD to Phase 0 before any customer data is onboarded.

- Design and testing are about 38% of feature effort overall (per-feature testing in Phases 0–2). Phase 3 stays thinner, so a 6 MD testing uplift (†) is planned there.

- Load by phase: Phase 0 51.7 MD, Phase 1 73.7 MD, Phase 2 77.6 MD, Phase 3 60.5 MD, Phase 4 58.3 MD. The peak is Phase 2 at about 3.9 FTE; the plan is loaded between 2.6 and 3.9 FTE.

- Phases 3 and 4 have totals only on the slide. Confirm the proposed itemisation and whether Phase 2 “LangGraph agentic workflows” already delivers the agent runtime planned in Phase 4.

- The GRL@PA app (Phase 1) and NEA Training Simulator (Phase 4) are ported as generic templates; onboarding the existing NEA app (which keeps its own hosting and bespoke models) to platform sign-in, audit and gateway services is in the backlog. The platform does not host GPU-driven models.

# 5  Beyond Phase 4 – Path to the Full Vision

Capabilities in the recommended architectures that are not in Phases 0–4, with indicative AI-assisted effort (including 20% buffer). Detailed vision estimates are in Appendix C of each solution document.

| Capability not covered by Phases 0–4 | Product | Indicative MD |
| --- | --- | --- |
| Critical security fixes from the as-built review (secret rotation and history purge, enforced fail-closed RLS, CI secret scanning) – recommended to add to Phase 0 | Shared core | 8 |
| Identity: multi-tenant Entra federation (External ID, other IdPs), SCIM, group-to-role mapping – extends the as-built Entra ID login and RBAC/ABAC | Shared core | 20 |
| A2A gateway (agent cards, auth, routing) | AI Gateway | 30 |
| Compliance: IM8 / NIST AI RMF evidence and SOC 2 readiness (Singapore pack, 45 MD); Malaysia, Thailand and Indonesia packs and SOC 2 Type I audit support (45 MD) | AI Gateway | 90 |
| EKS + Helm packaging; on-premises and air-gapped bundles | Shared core | 110 |
| Scale to 1,000 users / agents (asynchronous usage and audit writers, Valkey budget counters, load tests; cache scaling is done in Phase 2) | Shared core | 35 |
| Agent Builder UI (graph editor + code mode) and multi-agent orchestrator | AI Apps | 60 |
| Publishing (PWA, custom domains), evaluation gate and approvals | AI Apps | 35 |
| Integration Hub (credential vault, egress proxy, AWS / Azure / SAP connectors) | AI Apps | 40 |
| Activate AI Gateway piece and knowledge pieces (Bedrock KB, OpenSearch; connector wiring already in the Phase 1 generic knowledge tool) | AI Apps | 10 |
| Bespoke AI app onboarding (registration, SDK, identity and gateway integration, telemetry) | AI Apps | 30 |
| Dedicated LiteLLM proxy instance per silo tenant (own database, secret manager and cache namespace; isolation tier T2 in the RESPONSIBLE-AI multi-tenancy design) | AI Gateway | 12 |
| Supply-chain trust for AI-assisted delivery: reproducible build (hash-pinned dependencies, base image by digest, vendor checksums), signed CycloneDX SBOM and SLSA build provenance on every release, vulnerability scan with VEX statements, AI-BOM of models, guardrails and judges, customer verification guide (RESPONSIBLE-AI BACKLOG.md BL-01 and BL-02) | Shared core | 11 |
| Total (indicative) |  | 491 |

Phases 0–4 (≈ 321.8 MD) plus the backlog (≈ 491 MD) gives about 812.8 MD to the full platform vision with AI-assisted delivery.